## NNICB FOI 1608 Action Log
NNICB FOI 1608
Workstream | Task list | Actions taken | By whom? | Deadline | Comments/Discussion | Challenges | Status update | Date completed | Not started | In progress | Complete
| Confirm everybody has received the NatPSA alert published Tuesday 28th November | Email sent to MSO leads across the ICS 29/11/23 | ICB | 2023-11-30 | Identified relevant stakeholders required from paediatrics and adult neurology/MH teams. Pain management consultants. Specialist pharmacists/nurses/techs. PCN representation. |  | Complete | 2023-12-01
| Identify executive lead | Identified | ICB | 2023-12-08 | Need to link with Quality Directorate and MOPB |  | Complete | 2023-12-07
| Create a stakeholder contact list |  | ICB | 2023-11-08 |  |  | In progress
| Identify patients with lived experience |  | Trusts/PCN/Pain Team | 2023-12-15
Communication and planning | Create new or existing group with relevant stakeholders to co-ordinate the implementation of the new regulatory measures in providers, with oversight from a senior quality group. |  | ICB | 2023-12-15
| Appoint chair for meeting | Identified | ICB | 2023-12-15 |  |  | Complete | 2023-12-07
| Meeting invites to go out | Agreed 13th December 9-11am and 24th January 9-11am | ICB | 2023-12-08 |  |  | Complete | 2023-12-08
| Meeting invite for 10th January |  | ICB | 2023-12-15 | Following initial meeting it was felt that an additional meeting would be required to discuss progress, before the final assurance meeting on 24th Jan prior to submission. |  | Complete | 2023-12-14
| Agenda for 10th January |  | ICB | 2024-01-08
| https://forms.office.com/e/tYyRQXqm9H for completion 5pm 18.01.24 |  | ICB | 2024-01-18 | There are two main questions. 1) Who in your system will have overall responsibility for implementing the actions of the alert? (name and job role) 2) Will you have a designated group to co-ordinate the implementation of the new regulatory measures within your ICB in place by 31 January 2024? |  | Complete | 2023-12-22
| Communication methods across ICB | TeamNet communication - paragraph to be written | ICB | 2023-12-11
| Communication methods across ICB |  | ICB
| Communication methods across NUH |  | NUH
| Communication methods across SFHT |  | SFH
| Communication methods across NHCT | TMOG meeting agenda item on 11/12/23. action to set up internal working group for internal implementation of the alert. | NCHT
| Report back to MHRA and complete the declaration |  | ICB | 2023-01-31
| ICB standard operating procedure for Sodium Valproate | 2018 SOP updated in Feb-22 to bring in line with PPP update. | ICB |  |  | Clarification on what to do if primary care clinicians can't find ARAF in the patient records.
Consider APC updates required for sodium Valproate as a result of the NatPSA
Agreement on Risk acknowledgement form completion
To update all local guidance and protocols relating to prescribing of valproate to reflect the new regulatory position including definition of the roles and responsibilities of clinician and provider organisations and recordings of compliance with the risk forms | Agreement on how the risk acknowledgement forms will be visible to primary care clinicians
| Evidence of updated audit resources in line with NatPSA alert |  | NUH
| Evidence of guidance protocols updated |  | NUH
| Evidence of adherence to new ARAF requirements |  | NUH
| Evidence of updated audit resources in line with NatPSA alert |  | SFHT
| Evidence of guidance protocols updated |  | SFHT
| Evidence of adherence to new ARAF requirements |  | SFHT
| Evidence of updated audit resources in line with NatPSA alert |  | NHCT
| Evidence of guidance protocols updated |  | NHCT
| Evidence of adherence to new ARAF requirements |  | NHCT
| ICB population data for sodium valproate |  | ICB
Identify list of patients at risk of health inequalities
Potential number of patients on sodium valproate with learning difficulties
To commission work if necessary to understand the needs of the affected population, including those people most at risk of health inequalities. | consider population in whom English is not their first language
Providing access to those individuals who have no fixed abode
Prioritisation of high risk patients for highly effective contraception.
To commission/determine the local pathways of care for women of childbearing potential and girls in relation to the prescribing and review of valproate | Liaise with public health family planning clinics for prioritisation of high risk patients for highly effective contraception
| Results from existing primary care audit of patient on sodium valproate | Initial audit conducted in 2018, with follow up review completed between April-22 and Mar-23 | ICB |  | 460 patients reviewed across 3 PBPs. 151 patients under neurology or mental health team. 75 ARAF in place. 74 required referral to MH or neurology team. 107 on highly effective contraception. | Clarification on what to do if primary care clinicians can't find ARAF in the patient records.
Results from existing SFHT audit on patients taking sodium valproate
To review the results of local audit(s) of compliance with the existing PPP measures for girls and women of childbearing potential prescribed valproate | Results from existing NUH audits on patients taking sodium valproate
Results from NHCT audit on patients sodium valproate
| Discussion of next steps and future audit in light of NatPSA |  | All
National Resources adaption/adoption
Future clinical resources
To plan for and identification of clinical resource to meet the identified needs of the population and implement the new regulatory measures. | Challenges and risk